## issues1 2
issue number | title | state | author | createdAt | Action | Report to TC? | Board | Old components/nets | New components/nets
79 | extraneous net: DFF_REF_CLK_P/N<0/1> ? | OPEN | strilov | 2026-08-10 10:57 | Removed superfluous nets. No change to netlist | No | Main | DFF_REF_CLK_P/N<0/1> | None (deleted)
78 | backplane JTAG connection | OPEN | strilov | 2026-08-10 10:50 | Removed b/plane connections to MMC. Connected to FPGA via switches | Yes | Main | None | TE1
77 | MIB JTAG daughter board USB-C-SFP inteference | OPEN | strilov | 2026-04-02 14:20 | Awkward rather than impossible. Closing issue with "won't fix" | No | JTAG
75 | Rename nets on JTAG serial board - they are the wrong way round | OPEN | DavidCussans | 2026-01-23 17:24 | Closing without action as a duplicate on issue #68 and issue #74 | No | JTAG
74 | Rename nets on MIB v3 main board now that UART and LEDs have been moved to AUX-IO connector ( J4 ) | OPEN | DavidCussans | 2026-01-22 13:55 | UART connections addressed in #68. Edited LED nets as well. | Yes (minor change) | Main
73 | look at front GPIO to/from FPGA | OPEN | strilov | 2025-12-18 15:35 | Added U/FL connectors on JTAG d/board (no room on f/panel) | Yes | JTAG | None
72 | FTDI UART FPGA integration | OPEN | strilov | 2025-12-08 10:26 | Closed - needed firmware fix | No | Main | N/A
71 | SFP I2C not working | OPEN | strilov | 2025-12-08 09:31 | Closed - needed firmware fix | No |  | N/A | N/A
70 | Add fuse to JTAG Vref_jtag line | OPEN | DavidCussans | 2025-11-12 11:42 | Done. Added fuse. | Yes | Main | None | FS3
69 | Separate fuses for 3.3V and 2.5V DC-DC converters | OPEN | DavidCussans | 2025-11-10 12:13 | No longer needed. Fuse added to Vref_JTAG. Close with no action | No | Main | N/A | N/A
68 | UART/AUXIO signal labels | OPEN | strilov | 2025-10-29 12:50 | Done. Changed net-names. | Yes (minor change)
67 | D-FF on SFP[2] needs pull-down for PECL outputs | OPEN | DavidCussans | 2025-10-24 10:05 | "Y" termination scheme implemented. | Yes | Main
66 | Resistor location | OPEN | strilov | 2025-10-03 12:18 | R55 moved. | Yes | Main | R55 | R55
65 | JTAG daugherboard outline is too big | OPEN | DavidCussans | 2025-08-19 14:36 | Edited outline. | Yes (minor change) | JTAG
60 | Front panel switch , SW1 , is 180-degrees wrong rotation | OPEN | DavidCussans | 2025-02-24 10:13 | Checked. Rotated w.r.t v215. Good. Closed | Yes | Main | SW1 | SW1
59 | Indicator LEDs , DS1 , DS2 ( red, blue ) have incorrect part numbers. D4 (red) is obsolete | OPEN | DavidCussans | 2025-02-17 14:54 | Replaced blue LED. Other obsolete LEDs are 0603 so fix manually in BoM | Yes(minor change) | Main
58 | R60 (voltage set on 2.5V) on MIB v3 (pre-production MIB) wrong value. | OPEN | DavidCussans | 2025-02-04 13:43 | Fixed in schematic and PCB | Yes | Main
57 | IC5 on MIB v3 (pre-production MIB) assembled incorrectly | OPEN | DavidCussans | 2025-02-04 12:16 | Fixed confusing silk | Yes(minor change) | Main
50 | Swap differential pairs to allocate each upstream SFP I/O to a separate bank/clock region on FPGA | OPEN | DavidCussans | 2024-08-16 13:41 | Checked and MIBv3 routing OK. Duplicate f #42 | No | Main
42 | Check that data received from SFPs goes to clock capable pins | OPEN | DavidCussans | 2024-07-23 08:44 | Checked and MIBv3 routing OK. Duplicate f #50 | No | Main
54 | Swap pins 1,3,5 of J4 from GND to VCC3v3 ( to allow powering of LEDs on daughter board) | CLOSED | DavidCussans | 2024-08-28 11:57
51 | Attach SMD test pad to ATMEGA128 UART0 transmit pin ( PE1 ) to give us more debug options. | CLOSED | DavidCussans | 2024-08-16 14:01
47 | Move red and green LEDs to "standard" positions for Schroff/nvent front panel mechanism. Remove existing light-pipe and rely on front panel mechanism | CLOSED | DavidCussans | 2024-07-31 16:36
45 | Check to see if data from Endpoints arrives on clock-capable pins on FPGA. | CLOSED | DavidCussans | 2024-07-23 09:30
44 | Move blue LED to correct position to follow uTCA standard. | CLOSED | DavidCussans | 2024-07-23 09:27
41 | One mounting block for tongue-2 PCB needs to have recess milled to avoid C188/C189 | CLOSED | DavidCussans | 2024-07-22 16:58
40 | Pull ADR0 pin on the LT2991 voltage sensor high (rather than low) | CLOSED | DavidCussans | 2024-07-19 13:39
39 | All I2C current/voltage/temperatures sensors should be powered from MP3V3 , not just the temperature sensor. | CLOSED | DavidCussans | 2024-07-03 16:09
37 | dcdc_2v5_pg line should be moved from PE6 to PF1 | CLOSED | DavidCussans | 2024-07-03 14:07
36 | PRESENCE_12V line ( currently connected to PA1 ) should be connected to PF0 . | CLOSED | DavidCussans | 2024-07-03 14:04
34 | uTCA handle almost shorts to C51. Move C51 | CLOSED | DavidCussans | 2024-07-03 12:44
25 | Replace board-sense diode (D12) with Schottky version. Move R102 so that diode can be completely decoupled from MMC uController | CLOSED | DavidCussans | 2024-05-29 06:24
24 | Add 12V power connector to allow easy powering on bench | CLOSED | DavidCussans | 2024-01-08 10:50
23 | Replace DNF resistors R81,R83 with 100nF capacitors | CLOSED | DavidCussans | 2023-12-15 12:25
22 | Add fuses to main 12V and 3.3V management power line from backplane | CLOSED | DavidCussans | 2023-12-15 11:52
21 | Alter RESET line on MMC uController so that uController can be programmed with MIB out of crate | CLOSED | DavidCussans | 2023-12-15 11:49
20 | Replace 0.1-inch header for MMC uController programming with 0.05-inch header (to match modern cables) | CLOSED | DavidCussans | 2023-12-13 11:46
19 | Allow AVR programming cable to override RESET line from uTCA backplane | CLOSED | DavidCussans | 2023-12-13 10:45
18 | Remove D-FF from two upstream SFPs. Add mux to allow either direct or via D-FF on third | CLOSED | DavidCussans | 2023-12-13 10:43